## 📋 Overview
🚀 TTeamFlow — Project Development Plan
Deadline: 10/10/2026 ¦ Start: 01/09/2026 ¦ Team: QuanNH · PhongVV · KienTT ¦ Total sprints: 6
# | Task Name | Assigned To | Start | Deadline | Priority | Notes | Type | Status
Sprint 1 ¦ Sep 01 – Sep 07 ¦ Foundation & Database
1 | Tạo Prisma migrations + seed data | QuanNH | Sep 01 | Sep 03 | 🔴 HIGH | npx prisma migrate dev, commit migration files | BE | TODO
2 | Users: update profile (avatar, phone) | QuanNH | Sep 03 | Sep 05 | 🟡 MED | PATCH /api/v1/users/me, DTO UpdateProfileDto | BE | TODO
3 | Comments module: CRUD | PhongVV | Sep 01 | Sep 05 | 🔴 HIGH | GET/POST/PATCH/DELETE /projects/:id/tasks/:id/comments | BE | TODO
4 | Checklists module: CRUD + toggle | PhongVV | Sep 04 | Sep 07 | 🔴 HIGH | POST/PATCH/DELETE /tasks/:id/checklists/:cid, toggle endpoint | BE | TODO
5 | App layout: sidebar + header + routing | KienTT | Sep 01 | Sep 05 | 🔴 HIGH | Sidebar nav, top header, responsive, dark/light toggle | FE | TODO
6 | Register page | KienTT | Sep 05 | Sep 07 | 🔴 HIGH | Form đăng ký, gọi POST /auth/register | FE | TODO
Sprint 2 ¦ Sep 08 – Sep 14 ¦ Core Backend Features
7 | Projects: update + archive | QuanNH | Sep 08 | Sep 10 | 🔴 HIGH | PATCH /projects/:id, POST /projects/:id/archive | BE | TODO
8 | Project members: update role + remove | PhongVV | Sep 08 | Sep 10 | 🟡 MED | PATCH /projects/:pid/members/:uid, DELETE same | BE | TODO
9 | Tasks: update + soft delete + list | PhongVV | Sep 08 | Sep 12 | 🔴 HIGH | PATCH /tasks/:id, DELETE, GET /projects/:id/tasks?column= | BE | TODO
10 | Task assignment: add/remove assignee | PhongVV | Sep 11 | Sep 14 | 🟡 MED | POST/DELETE /tasks/:id/assignments | BE | TODO
11 | Kanban: reorder columns | QuanNH | Sep 10 | Sep 12 | 🟡 MED | PATCH /projects/:id/columns/reorder body: [{id,position}] | BE | TODO
12 | Activity log: ghi log tự động tất cả service | QuanNH | Sep 12 | Sep 14 | 🟡 MED | Ghi log cho project/member/task events | BE | TODO
Sprint 3 ¦ Sep 15 – Sep 21 ¦ Frontend Core Pages
13 | Projects page: create + edit + archive UI | KienTT | Sep 15 | Sep 18 | 🔴 HIGH | Modal tạo project, menu edit, confirm archive | FE | TODO
14 | Dashboard page: metrics + charts | KienTT | Sep 15 | Sep 19 | 🔴 HIGH | Progress bar, stat cards, member workload list | FE | TODO
15 | Members management page | KienTT | Sep 18 | Sep 21 | 🟡 MED | List, invite, change role, remove member | FE | TODO
16 | User profile page | KienTT | Sep 19 | Sep 21 | 🟢 LOW | Hiện thông tin, form update profile + avatar | FE | TODO
17 | Admin: list users + toggle isActive | QuanNH | Sep 15 | Sep 17 | 🟡 MED | GET /admin/users, PATCH /admin/users/:id/toggle | BE | TODO
Sprint 4 ¦ Sep 22 – Sep 28 ¦ Frontend Features
18 | Kanban: drag-and-drop task (DnD Kit) | KienTT | Sep 22 | Sep 25 | 🔴 HIGH | @dnd-kit/sortable, gọi PATCH /tasks/:id/move | FE | TODO
19 | Task detail modal / side panel | KienTT | Sep 22 | Sep 26 | 🔴 HIGH | Title, desc, priority, dates, assignees, labels | FE | TODO
20 | Checklist UI trong task modal | PhongVV | Sep 22 | Sep 25 | 🔴 HIGH | Add item, toggle done, delete, progress bar | FE | TODO
21 | Comments UI trong task modal | PhongVV | Sep 24 | Sep 27 | 🔴 HIGH | Danh sách comment, form thêm, edit/delete own | FE | TODO
22 | Kanban: thêm/rename/xoá cột custom | KienTT | Sep 26 | Sep 28 | 🟡 MED | Inline edit column name, add column button | FE | TODO
23 | Admin panel: quản lý user | KienTT | Sep 26 | Sep 28 | 🟡 MED | Chỉ hiển thị khi systemRole=ADMIN | FE | TODO
Sprint 5 ¦ Sep 29 – Oct 05 ¦ Polish & Integration
24 | Activity log UI trong project | KienTT | Sep 29 | Oct 01 | 🟡 MED | Timeline feed, icon theo action type | FE | TODO
25 | Toast notifications + error boundaries | KienTT | Sep 29 | Oct 01 | 🟡 MED | react-hot-toast hoặc sonner, global error page | FE | TODO
26 | Responsive + mobile layout | KienTT | Oct 01 | Oct 03 | 🟢 LOW | Sidebar collapse, mobile kanban scroll | FE | TODO
27 | Integration test: luồng end-to-end | QuanNH | Sep 29 | Oct 03 | 🔴 HIGH | Login→project→task→kanban→comment | ALL | TODO
28 | Xử lý edge case & lỗi nghiệp vụ | PhongVV | Sep 29 | Oct 03 | 🔴 HIGH | Archived project read-only, permission guard check | ALL | TODO
29 | Performance: query optimize + lazy load | QuanNH | Oct 03 | Oct 05 | 🟡 MED | Prisma select fields, pagination task list | ALL | TODO
Sprint 6 ¦ Oct 06 – Oct 10 ¦ Final QA & Deployment
30 | Docker compose test + staging deploy | QuanNH | Oct 06 | Oct 08 | 🔴 HIGH | docker compose up --build, run migrations, seed | DEVOPS | TODO
31 | CI fix & branch protection rules | QuanNH | Oct 06 | Oct 07 | 🟡 MED | Require PR review trước merge main | DEVOPS | TODO
32 | Bug fix round | PhongVV | Oct 07 | Oct 09 | 🔴 HIGH | Từ kết quả test sprint 5 | ALL | TODO
33 | Final PR review & merge develop→main | QuanNH | Oct 09 | Oct 10 | 🔴 HIGH | Code review toàn bộ, merge release | ALL | TODO
34 | Demo & handover documentation | KienTT | Oct 09 | Oct 10 | 🟡 MED | Update README, demo video/screenshot | ALL | TODO

## 👥 Member Workload
👥 Member Workload Summary
# | Member | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Focus Area
1 | QuanNH | 2 | 3 | 2 | 0 | 2 | 3 | Backend Lead · DevOps · Auth · Migration · CI
2 | PhongVV | 2 | 3 | 1 | 3 | 2 | 1 | Backend Features · Comments · Checklists · Bug fix
3 | KienTT | 2 | 0 | 3 | 4 | 3 | 1 | Frontend · UI/UX · Kanban DnD · Dashboard
| TOTAL TASKS | 4 | 6 | 6 | 7 | 7 | 5

## 📅 Timeline
📅 Sprint Timeline — Sep 01 to Oct 10
Member | Sep 01-07 | Sep 08-14 | Sep 15-21 | Sep 22-28 | Sep 29-Oct 05 | Oct 06-10 | Focus
🧑‍💻 QuanNH | Migration + Profile API | Projects update/archive + Kanban reorder + Activity log | Admin API | (review) Integration test | Integration test + Performance | Docker deploy + Final merge | Backend Lead · DevOps
👨‍💻 PhongVV | Comments module + Checklists module | Tasks CRUD + Assignment API + Member role | (review) Edge cases | Checklist UI + Comments UI | Edge case + Bug fix | Bug fix round | Backend Features
🎨 KienTT | App layout + Register page | (review) | Projects UI + Dashboard + Members page + Profile | Kanban DnD + Task modal + Column manage + Admin panel | Activity log UI + Toast + Responsive | Demo + Docs | Frontend
⚠️ DEADLINE: Oct 10, 2026

## ✅ PR Checklist
✅ Pull Request Checklist (theo README)
# | Checklist Item | Required? | Notes
1 | Build pass (CI green) | ✅ Bắt buộc | GitHub Actions phải xanh trước khi merge
2 | Lint pass (0 error) | ✅ Bắt buộc | npm run lint không có lỗi
3 | DTO có validation decorator | ✅ Bắt buộc | class-validator @IsString, @IsEmail...
4 | Không expose passwordHash/tokenHash | ✅ Bắt buộc | Dùng Prisma select để loại trừ
5 | API có guard đúng (JWT + Role) | ✅ Bắt buộc | @ProjectRoles hoặc @SystemRoles
6 | Migration đi kèm nếu sửa schema | ✅ Bắt buộc | npx prisma migrate dev
7 | Không sửa migration đã merge | ✅ Bắt buộc | Tạo migration mới nếu cần thay đổi
8 | Có xử lý error nghiệp vụ (throw exceptions) | ✅ Bắt buộc | NotFoundException, BadRequestException...
9 | Không query DB trực tiếp trong Controller | ✅ Bắt buộc | Controller → Service → Prisma
10 | Không hardcode URL/secret | ✅ Bắt buộc | Dùng ConfigService hoặc env()
11 | Ít nhất 1 người (QuanNH) approve | ✅ Bắt buộc | Không tự merge PR của mình
12 | Self-review trước khi tạo PR | 🟡 Recommended | Đọc lại diff, kiểm tra logic
13 | Update README nếu có thay đổi lớn | 🟡 Recommended | Đặc biệt khi thêm env var mới